## Causes Analysis
|  | Gráfica más abajo |  |  |  | 1ST. DEADLINE | 2ND. INAPPROPRIATE PLANNING | 3RD. NOT EFFECTIVE PROJECT MANAGEMENT | 4TH. PRODUCING MORE WITHOUT QUALITY | 5TH. LACK OF QUALIFIED PROFESSIONALS | 6TH. INACCURATE TIME ESTIMATE | 7TH. LACK OF A WELL-DEFINED PROCESS
4 | MANAGEMENT | LACK OF A WELL-DEFINED PROCESS | 9 | 268 | MANAGEMENT | 7.836% | 3.358% | 5.97% | 3.358% | 4.478% | 3.358% | 3.358%
5 | MANAGEMENT | INAPPROPRIATE PLANNING | 9 |  | ARCHITECT | 6.787% | 6.787% | 5.43% | 6.335% | 4.525% | 2.715% | 2.715%
3 | MANAGEMENT | LACK OF QUALIFIED PROFESSIONALS | 12 |  | TECHNICAL | 9.413% | 4.502% | 3.956% | 3.683% | 3.547% | 3.547% | 3.001%
2 | MANAGEMENT | NOT EFFECTIVE PROJECT MANAGEMENT | 16
1 | MANAGEMENT | DEADLINE | 21 |  | MANAGEMENT | 21 | 9 | 16 | 9 | 12 | 9 | 9
5 | ARCHITECT | LACK OF QUALIFIED PROFESSIONALS | 10 | 221 | ARCHITECT | 15 | 15 | 12 | 14 | 10 | 6 | 6
4 | ARCHITECT | NOT EFFECTIVE PROJECT MANAGEMENT | 12 |  | TECHNICAL | 69 | 33 | 29 | 27 | 26 | 26 | 22
3 | ARCHITECT | PRODUCING MORE WITHOUT QUALITY | 14
1 | ARCHITECT | INAPPROPRIATE PLANNING | 15
2 | ARCHITECT | DEADLINE | 15
5 | TECHNICAL | INACCURATE TIME ESTIMATE | 26 | 733
4 | TECHNICAL | PRODUCING MORE WITHOUT QUALITY | 27
3 | TECHNICAL | NOT EFFECTIVE PROJECT MANAGEMENT | 29
2 | TECHNICAL | INAPPROPRIATE PLANNING | 33
1 | TECHNICAL | DEADLINE | 69
| 10 | LACK OF TECHNICAL KNOWLEDGE | 2.619%
| 9 | LACK OF EXPERIENCE | 2.782%
| 8 | NON-ADOPTION OF GOOD PRACTICES | 3.028%
| 7 | LACK OF A WELL-DEFINED PROCESS | 3.11%
| 6 | INACCURATE TIME ESTIMATE | 3.355%
| 5 | LACK OF QUALIFIED PROFESSIONALS | 3.928%
| 4 | PRODUCING MORE WITHOUT QUALITY | 4.173%
| 3 | NOT EFFECTIVE PROJECT MANAGEMENT | 4.664%
| 2 | INAPPROPRIATE PLANNING | 4.664%
| 1 | DEADLINE | 8.838%
| 1 | DEADLINE | 108 | 8.838%
| 2 | INAPPROPRIATE PLANNING | 57 | 13.5%
| 3 | NOT EFFECTIVE PROJECT MANAGEMENT | 57 | 18.17%
| 4 | PRODUCING MORE WITHOUT QUALITY | 51 | 22.34%
| 5 | LACK OF QUALIFIED PROFESSIONALS | 48 | 26.27%
| 6 | INACCURATE TIME ESTIMATE | 41 | 29.62%
| 7 | LACK OF A WELL-DEFINED PROCESS | 38 | 32.73%
| 8 | NON-ADOPTION OF GOOD PRACTICES | 37 | 35.76%
| 9 | LACK OF EXPERIENCE | 34 | 38.54%
| 10 | LACK OF TECHNICAL KNOWLEDGE | 32 | 41.16%
| 11 | PRESSURE | 28
| 12 | INAPPROPRIATE / POORLY PLANNED / POORLY EXECUTED TEST | 26
| 13 | BAD DESIGN | 24
| 14 | LACK OF TEAM COMMUNICATION | 23
| 15 | TEAM OVERLOAD | 23
| 16 | COST | 22
| 17 | INACCURATE OR COMPLEX REQUIREMENT | 20
| 18 | CHANGE OF REQUIREMENTS | 19
| 19 | HIGH TURNOVER OF THE TEAM | 19
| 20 | LACK OF PERCEPTION OF THE IMPORTANCE OF TESTING AND REFACTORING | 19
| 21 | LACK OF COMMITMENT | 18
| 22 | LACK OF KNOWLEDGE ON DEVELOPMENT TOOLS | 18
| 23 | CUSTOMER DOES NOT KNOW HIS OWN NEEDS | 17
| 24 | LACK OF TRAINING | 17
| 25 | PROBLEMS IN ARCHITECTURE | 16
| 26 | SLOPPY CODE | 16 |  |  | 4 | MANAGEMENT | LACK OF A WELL-DEFINED PROCESS |  |  |  | 3.358%
| 27 | LACK OF DOMAIN KNOWLEDGE | 15 |  |  | 5 | MANAGEMENT | INAPPROPRIATE PLANNING |  |  |  | 3.358%
| 28 | POOR ALLOCATION OF RESOURCES | 14 |  |  | 3 | MANAGEMENT | LACK OF QUALIFIED PROFESSIONALS |  |  |  | 4.478%
| 29 | POOR SCOPE DEFINITION | 14 |  |  | 2 | MANAGEMENT | NOT EFFECTIVE PROJECT MANAGEMENT |  |  |  | 5.97%
| 30 | MANAGER'S LACK OF AWARENESS OF CUSTOMER NEEDS | 13 |  |  | 1 | MANAGEMENT | DEADLINE |  |  |  | 7.836%
| 31 | LACK OF CODE REVIEW | 12 |  |  | 5 | ARCHITECT | LACK OF QUALIFIED PROFESSIONALS |  |  |  | 4.525%
| 32 | OUTDATED / INCOMPLETE DOCUMENTATION | 12 |  |  | 4 | ARCHITECT | NOT EFFECTIVE PROJECT MANAGEMENT |  |  |  | 5.43%
| 33 | TEST NOT PERFORMED | 12 |  |  | 3 | ARCHITECT | PRODUCING MORE WITHOUT QUALITY |  |  |  | 6.335%
| 34 | EXTERNAL COMPONENT DEPENDENCY | 11 |  |  | 1 | ARCHITECT | INAPPROPRIATE PLANNING |  |  |  | 6.787%
| 35 | INADEQUATE IMPACT AND RISK ANALYSIS | 11 |  |  | 2 | ARCHITECT | DEADLINE |  |  |  | 6.787%
| 36 | REQUIREMENTS ELICITATION ISSUES | 11 |  |  | 5 | TECHNICAL | INACCURATE TIME ESTIMATE |  |  |  | 3.547%
| 37 | ADOPTION OF CONTOUR SOLUTIONS AS DEFINITIVE | 10 |  |  | 4 | TECHNICAL | PRODUCING MORE WITHOUT QUALITY |  |  |  | 3.683%
| 38 | CHANGE OF SCOPE | 10 |  |  | 3 | TECHNICAL | NOT EFFECTIVE PROJECT MANAGEMENT |  |  |  | 3.956%
| 39 | COMPLEXITY OF THE PROJECT | 10 |  |  | 2 | TECHNICAL | INAPPROPRIATE PLANNING |  |  |  | 4.502%
| 40 | LACK OF REFACTORING | 10 |  |  | 1 | TECHNICAL | DEADLINE |  |  |  | 9.413%
| 41 | - | 9
| 42 | BAD TECHNICAL LEADERSHIP | 9
| 43 | INADEQUATE CHOICE OF TECHNOLOGY / TOOL / PLATFORM | 9
| 44 | LACK OF KNOWLEDGE | 9
| 45 | LACK OF REQUIREMENTS ANALYSIS | 9
| 46 | NON-COMPLIANCE WITH NON-FUNCTIONAL REQUIREMENTS | 9
| 47 | LACK OF SPECIFIC TEAM | 8
| 48 | LACK OF MOTIVATION | 7
| 49 | LACK OF QUALITY | 7
| 50 | LACK OF VALIDATION | 7
| 51 | NONEXISTENT DOCUMENTATION | 7
| 52 | REQUIRED INFRASTRUCTURE UNAVAILABLE | 7
| 53 | CUSTOMER DOES NOT LISTEN TO PROJECT TEAM | 6
| 54 | NON-COMPLIANCE WITH POLICIES ESTABLISHED BY MANAGEMENT | 6
| 55 | DEVELOPERS DO NOT LIKE TO DO SOME ACTIVITIES | 5
| 56 | LACK OF REUSE PRACTICES | 5
| 57 | POORLY CRAFTED SLAS | 5
| 58 | STRUCTURAL CHANGE IN THE COMPANIES INVOLVED | 5
| 59 | THE COMPANY DOES NOT GIVE IMPORTANCE TO DOCUMENTATION | 5
| 60 | DISCONTINUED COMPONENT | 4
| 61 | INADEQUATE MANAGEMENT DECISION | 4
| 62 | LACK OF AUTOMATED TESTING | 4
| 63 | LACK OF TRANSPARENCY BETWEEN CLIENT AND DEVELOPMENT TEAM | 4
| 64 | POOR CHOICE OF FRAMEWORK | 4
| 65 | THIRD PARTY TEAM INVOLVED IN THE PROJECT | 4
| 66 | CHANGE IN EXTERNAL COMPONENT | 3
| 67 | INADEQUATE DATA MODEL | 3
| 68 | INSUFFICIENT LONG-TERM VISION | 3
| 69 | LACK OF INFORMATION | 3
| 70 | POOR DESIGN | 3
| 71 | POOR TECHNICAL MANAGEMENT | 3
| 72 | REQUIREMENTS DEFINITION ISSUES | 3
| 73 | BE RESPONSIBLE FOR CODE FROM OTHERS | 2
| 74 | CONCERN WITH JUST BACK-END DEVELOPMENT | 2
| 75 | DEPLOYMENT | 2
| 76 | LACK OF CUSTOMER COMMITMENT | 2
| 77 | LACK OF INTEREST IN ACQUIRING KNOWLEDGE | 2
| 78 | LACK OF PAIR PROGRAMMING | 2
| 79 | LACK OF TRACEABILITY OF BUGS | 2
| 80 | LOW PRODUCTIVITY | 2
| 81 | NON-SHARING OF KNOWLEDGE | 2
| 82 | POOR TECHNICAL LEADERSHIP | 2
| 83 | VERSION INCOMPATIBILITY | 2
| 84 | AVOID CHANGES IN WORKING CODE | 1
| 85 | CHANGE IN DESIGN | 1
| 86 | CUSTOMER DOES NOT WILLING TO PAY | 1
| 87 | ESTABLISHED TIME PERIODS | 1
| 88 | EXTERNAL COMPONENT LIMITATION | 1
| 89 | FEAR TO GIVE AN OPINION | 1
| 90 | INADEQUATE TECHNICAL DECISION | 1
| 91 | INTEGRATION OF NEW TOOLS | 1
| 92 | LACK OF CHANGE CONTROL | 1
| 93 | LACK OF CONFIDENCE IN THE DEVELOPMENT | 1
| 94 | LACK OF CONFIDENCE IN THE PRODUCT | 1
| 95 | LACK OF IT GOVERNANCE | 1
| 96 | LACK OF PERCEPTION OF THE IMPORTANCE OF AUTOMATED TESTS | 1
| 97 | LACK OF PERCEPTION OF THE IMPORTANCE OF DEALING WITH TD | 1
| 98 | LACK OF PRIORITIZATION AT COMPANY LEVEL | 1
| 99 | LACK OF PRIORITY FOR THE PROJECT | 1
| 100 | LACK OF PROTOTYPING | 1
| 101 | LACK OF UNDERSTANDING | 1
| 102 | LEGACY SYSTEM | 1
| 103 | LOW QUALITY | 1
| 104 | NO BUG FIXES | 1
| 105 | NORMATIVE CHANGES | 1
| 106 | OVER DOCUMENTATION | 1
| 107 | OVER PROJECT PLANNING | 1
| 108 | POLITICS IN THE BUSINESS | 1
| 109 | THE COMPANY DOES NOT GIVE IMPORTANCE TO QUALITY | 1
| 110 | UNNECESSARY DOCUMENTATION | 1
| 111 | UPDATING EXISTING TOOLS | 1
1222

## Hoja3
DEADLINE | 69
INAPPROPRIATE PLANNING | 33
NOT EFFECTIVE PROJECT MANAGEMENT | 29
FOCUS ON PRODUCING MORE AT THE EXPENSE OF QUALITY | 27
INACCURATE TIME ESTIMATE | 26
LACK OF QUALIFIED PROFESSIONALS | 26
LACK OF TECHNICAL KNOWLEDGE | 22
LACK OF A WELL-DEFINED PROCESS | 22
LACK OF EXPERIENCE | 20
NON-ADOPTION OF GOOD PRACTICES | 20
LACK OF TEAM COMMUNICATION | 17
PRESSURE | 15
BAD DESIGN | 15
TEAM OVERLOAD | 14
INAPPROPRIATE / POORLY PLANNED / POORLY EXECUTED TEST | 13
INACCURATE OR COMPLEX REQUIREMENT | 13
CUSTOMER DOES NOT KNOW HIS OWN NEEDS | 12
LACK OF KNOWLEDGE ON DEVELOPMENT TOOLS | 12
LACK OF TRAINING | 11
LACK OF COMMITMENT | 11
PROBLEMS IN ARCHITECTURE | 11
LACK OF DOMAIN KNOWLEDGE | 11
SLOPPY CODE | 10
POOR ALLOCATION OF RESOURCES | 10
LACK OF PERCEPTION OF THE IMPORTANCE OF TESTING AND REFACTORING | 9
INADEQUATE IMPACT AND RISK ANALYSIS | 9
HIGH TURNOVER OF THE TEAM | 9
COST | 8
COMPLEXITY OF THE PROJECT | 8
CHANGE OF REQUIREMENTS | 8
LACK OF REQUIREMENTS ANALYSIS | 8
TEST NOT PERFORMED | 8
NONEXISTENT DOCUMENTATION | 7
LACK OF CODE REVIEW | 7
ADOPTION OF CONTOUR SOLUTIONS AS DEFINITIVE | 7
LACK OF QUALITY | 7
OUTDATED / INCOMPLETE DOCUMENTATION | 6
INADEQUATE CHOICE OF TECHNOLOGY / TOOL / PLATFORM | 6
LACK OF VALIDATION | 6
LACK OF REFACTORING | 6
MANAGER'S LACK OF AWARENESS OF CUSTOMER NEEDS | 6
LACK OF SPECIFIC TEAM | 6
POOR SCOPE DEFINITION | 6
REQUIREMENTS ELICITATION ISSUES | 5
REQUIRED INFRASTRUCTURE UNAVAILABLE | 5
NON-COMPLIANCE WITH NON-FUNCTIONAL REQUIREMENTS | 5
BAD TECHNICAL LEADERSHIP | 5
CHANGE OF SCOPE | 5
5
EXTERNAL COMPONENT DEPENDENCY | 5
LACK OF KNOWLEDGE | 5
THE COMPANY DOES NOT GIVE IMPORTANCE TO DOCUMENTATION | 4
POORLY CRAFTED SLAS | 4
LACK OF MOTIVATION | 4
POOR DESIGN | 3
CUSTOMER DOES NOT LISTEN TO PROJECT TEAM | 3
LACK OF PERCEPTION OF THE IMPORTANCE OF TESTING, DOCUMENTING AND REFACTORING | 3
LACK OF TRANSPARENCY BETWEEN CLIENT AND DEVELOPMENT TEAM | 3
NON-COMPLIANCE WITH POLICIES ESTABLISHED BY MANAGEMENT | 3
CHANGE IN EXTERNAL COMPONENT | 3
DISCONTINUED COMPONENT | 2
LACK OF INFORMATION | 2
REQUIREMENTS DEFINITION ISSUES | 2
THIRD PARTY TEAM INVOLVED IN THE PROJECT | 2
POOR CHOICE OF FRAMEWORK | 2
VERSION INCOMPATIBILITY | 2
LOW PRODUCTIVITY | 2
CONCERN WITH JUST BACK-END DEVELOPMENT | 2
LACK OF TRACEABILITY OF BUGS | 2
LACK OF REUSE PRACTICES | 2
INADEQUATE DATA MODEL | 2
INADEQUATE MANAGEMENT DECISION | 2
INSUFFICIENT LONG-TERM VISION | 2
LACK OF AUTOMATED TESTING | 2
DEVELOPERS DO NOT LIKE TO DO SOME ACTIVITIES | 2
DEADLINE | 1
OVER PROJECT PLANNING | 1
LACK OF PRIORITY FOR THE PROJECT | 1
INADEQUATE TECHNICAL DECISION | 1
INTEGRATION OF NEW TOOLS | 1
LACK OF INTEREST IN ACQUIRING KNOWLEDGE | 1
LACK OF A WELL DEFINED PROCESS | 1
UPDATING EXISTING TOOLS | 1
POLITICS IN THE BUSINESS | 1
STRUCTURAL CHANGE IN THE COMPANIES INVOLVED | 1
LACK OF PRIORITIZATION AT COMPANY LEVEL | 1
UNNECESSARY DOCUMENTATION | 1
BE RESPONSABLE FOR CODE FROM OTHERS | 1
DEPLOYMENT | 1
POOR TECHNICAL MANAGEMENT | 1
LACK OF PERCEPTION OF THE IMPORTANCE OF AUTOMATED TESTS | 1
CUSTOMER DOES NOT WILLING TO PAY | 1
LACK OF PROTOTYPING | 1
CHANGE IN DESIGN | 1
LACK OF PERCEPTION OF THE IMPORTANCE OF DEALING WITH TD | 1
LACK OF CHANGE CONTROL | 1
NON-SHARING OF KNOWLEDGE | 1
OVER DOCUMENTATION | 1
BE RESPONSIBLE FOR CODE FROM OTHERS | 1
FEAR TO GIVE AN OPINION | 1
AVOID CHANGES IN WORKING CODE | 1
FOCUS ON PRODUCING MORE AT THE EXPENSE OF QUALITY | 1